## Dashboard
Agency Artifact — Staffing & Capacity Dashboard
Scenario: Active + Prospective ¦ Forecast: 10/5/26 – 10/3/27 (52 weeks)
KEY METRICS
Phases counted in scenario | 43
Peak firm utilization | 120.3% | Week of 10/26/26
Average firm utilization | 30.35%
Weeks with any level understaffed | 17 | of 52 weeks
Weeks with any level in excess capacity | 46 | of 52 weeks
Total phase fees | 2591500 | All phases on Projects sheet
Total projected cost of planned hours | 1098015
Fee vs projected cost | 1493485 | Projected cost = 42% of fee
STAFFING OUTLOOK — peak utilization and FTE shortfall by time horizon
| Near-term (wks 1–12) |  | Mid-term (wks 13–24) |  | Long-range (wks 25–52)
Staff Level | Peak Util. | Peak FTE Short | Peak Util. | Peak FTE Short | Peak Util. | Peak FTE Short
Principal | 158.3% | 1.1667 | 56.67% | 0 | 3.333% | 0
Director | 118.8% | 0.1875 | 112.5% | 0.125 | 62.5% | 0
Senior Designer | 144.4% | 0.44444 | 44.44% | 0 | 0% | 0
Mid Level Designer | 90.28% | 0 | 44.44% | 0 | 27.78% | 0
Project Designer | 155.6% | 0.55556 | 166.7% | 0.66667 | 11.11% | 0
Firm total (net FTE) | 120.3% | 1.5069 | 72.88% | 0 | 19.49% | 0
Red = understaffed / hire-level shortfall; amber = excess capacity or minor shortfall. Detail by week: Timeline (heat map + phase bars) and Forecast.
HIRING SIGNALS BY STAFF LEVEL
Staff Level | Current FTE | Peak Utilization | Weeks Understaffed | Weeks Excess Capacity | Peak FTE Short | First Hire-Trigger Week | Hire-By Date | Recommendation
Principal | 2 | 158.3% | 6 | 41 | 1.1667 | 2026-10-05 | 2026-08-10 | Hire 2 FTE — start recruiting now
Director | 1 | 118.8% | 3 | 35 | 0.1875 | None | — | Monitor — short-term overload, no sustained hire need
Senior Designer | 1 | 144.4% | 6 | 45 | 0.44444 | None | — | Monitor — short-term overload, no sustained hire need
Mid Level Designer | 2 | 90.28% | 0 | 44 | 0 | None | — | No hire needed
Project Designer | 1 | 166.7% | 17 | 35 | 0.66667 | 2026-11-23 | 2026-09-28 | Hire 1 FTE — start recruiting now
Hire-by date = first week FTE shortfall reaches the hire trigger minus hiring lead time (both set on Assumptions). Utilization is demand ÷ capacity (capacity already reflects target utilization).
Formulas:
Hire-By Date = IF([Peak FTE Short]="None","—",[Peak FTE Short]-7*Assumptions!$B11)

## Assumptions
Agency Artifact — Staffing & Capacity Planner: Assumptions
Blue cells are inputs. Change them here and every other sheet recalculates.
Add custom phases in the first empty cell under the list — they appear in the Projects dropdown automatically.
FORECAST SETTINGS | [5 empty] | PHASE / MILESTONE LIST | TIMELINE HORIZONS
Forecast start (must be a Monday) | 2026-10-05 | OK — Monday |  |  |  | Phase | Near-term: through week # | 12
Scenario view | Active + Prospective | Active only = exclude prospective projects |  |  |  | Concept | Mid-term: through week # | 24
Prospective weighting | 100% | % of prospective hours counted in the forecast when included (e.g. 50% = probability-weight) |  |  |  | Entitlement | Long-range = mid-term end to week 52. Drives Timeline shading & Dashboard outlook.
Understaffed flag: utilization above | 100% | Weekly demand ÷ capacity above this = understaffed (red) |  |  |  | SD
Overstaffed flag: utilization below | 60% | Weekly demand ÷ capacity below this = excess capacity (amber) |  |  |  | DD | STAFF ROSTER (drives headcount)
Hire trigger: FTE shortfall ≥ | 0.5 | Shortfall (in FTEs) that counts as a hiring need |  |  |  | CD | Initials | Staff Level | FTE
Hiring lead time (weeks) | 8 | Weeks needed to recruit and onboard; used for the hire-by date |  |  |  | Bidding | PK | Principal | 1
[6 empty] | Permitting | DF | Principal | 1
STAFF LEVELS & CAPACITY | [5 empty] | CA | KJ | Director | 1
Staff Level | Billable Rate ($/hr) | Headcount (FTE) | Hours / FTE / Week | Target Utilization | Capacity (billable hrs/wk) | Master Plan | HL | Senior Designer | 1
Principal | 290 | 2 | 40 | 75% | 60 | Phase 3- Choices | EHH | Mid Level Designer | 1
Director | 250 | 1 | 40 | 80% | 32 | Phase 4- Final Master Plan | KD | Mid Level Designer | 1
Senior Designer | 200 | 1 | 40 | 90% | 36 | Phase 5- Execution Plan | XX | Project Designer | 1
Mid Level Designer | 175 | 2 | 40 | 90% | 72 | ASR 1
Project Designer | 135 | 1 | 40 | 90% | 36 | ASR 2 | Edit this list for hires, departures or part-time staff (FTE 0.5). Headcount above updates.
Total |  | 7 |  |  | 236 | ASR 3
Capacity = Headcount × Hours per FTE × Target Utilization. Use fractional FTEs for part-time staff or planned hires/departures.
LISTS (drive dropdowns)
Project Status | Scenario View
Active | Active only
Prospective | Active + Prospective
Inactive
WEEKLY UPDATE CHECKLIST
1. Projects: for each project, fill the shaded header row (No., Name, Status), then one phase row per phase — pick phase, start/end dates, fee and weekly hours per level.
2. Check that each header row's Input Check reads 'All OK'. Change a single phase's Status to Prospective if only that phase is unconfirmed.
3. Assumptions: update headcount / utilization for hires, departures or leave.
4. Assumptions: to roll the calendar forward, change the forecast start to a new Monday.
5. Review Dashboard outlook & hiring signals, and the Timeline heat map.

## Projects
Project & Phase Planner — weekly input sheet | [5 empty] | Total Phase Fees (excl. inactive): | 2591500 | STAFF HOURS PER WEEK × Weeks (col G) = hours pool
Each project is a shaded header row with its phases underneath (click +/- at left to collapse). Phase rows: pick the phase, enter a Start Date and EITHER Weeks or an End Date, the phase fee, and each person's hours PER WEEK. Hours/week × Weeks = that person's pool, which you then map to actual weeks on the Timeline tab. Blue = input.
PROJECT & PHASE INPUTS | [7 empty] | Principal | Principal | Director | Senior Designer | Mid Level Designer | Mid Level Designer | Project Designer | CALCULATED — HOURS, MAPPING & ECONOMICS (do not overwrite)
Project No. | Project Name | Phase / Milestone | Status | Start Date | End Date | Weeks | Phase Fee ($) | PK | DF | KJ | HL | EHH | KD | XX | Total Hours Pool (hrs/wk × weeks) | Hours Mapped (Timeline) | Left to Map | Principal Pool Hrs | Director Pool Hrs | Senior Designer Pool Hrs | Mid Level Designer Pool Hrs | Project Designer Pool Hrs | Projected Cost ($) | Fee vs Cost ($) | % of Fee Used | Scenario Weight | Input Check | Row Type | Weeks (num)
2256 | Marigold Promenade | Project total | Active | 2027-04-01 | 2027-10-05 |  | 43500 | [7 empty] | 81 | 80 | 1 | 27 | 54 | 0 | 0 | 0 | 21330 | 22170 | 49.03% |  | 1 to fix | Project | 0
2256 | Marigold Promenade | CA | Active | 2027-04-01 | 2027-10-05 | 27 | 43500 | 1 |  | 2 |  |  |  |  | 81 | 80 | 1 | 27 | 54 | 0 | 0 | 0 | 21330 | 22170 | 49.03% | 100% | Map hours on Timeline | Phase | 27
2348 | Fairhaven Senior Housing | Project total | Inactive |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2348 | Fairhaven Senior Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | Project total | Inactive |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2370 | Tamarack Housing | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | Project total | Inactive |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2458 | Summit Ridge Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2469 | Fairhaven Village | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2470 | Canyon Vista Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2489 | Harbor Mobility Hub | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2494 | Laurel Park Garden | Project total | Active |  |  |  | 88000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88000 | 0% |  | 3 to fix | Project | 0
2494 | Laurel Park Garden | CD | Active |  |  |  | 56000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 0% | 100% | Enter dates | Phase | 0
2494 | Laurel Park Garden | Permitting | Active |  |  |  | 6500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0% | 100% | Enter dates | Phase | 0
2494 | Laurel Park Garden | CA | Active |  |  |  | 25500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 0% | 100% | Enter dates | Phase | 0
2499 | Zephyr Creative Office | Project total | Active | 2026-10-12 | 2026-12-20 |  | 76500 | [7 empty] | 300 | 300 | 0 | 40 | 80 | 0 | 180 | 0 | 63100 | 13400 | 82.48% |  | All OK | Project | 0
2499 | Zephyr Creative Office | CD | Active | 2026-10-12 | 2026-12-20 | 10 | 76500 | 4 |  | 8 |  |  | 18 |  | 300 | 300 | 0 | 40 | 80 | 0 | 180 | 0 | 63100 | 13400 | 82.48% | 100% | OK | Phase | 10
2545 | Mariner Courtyard | Project total | Inactive |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2545 | Mariner Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2550 | Driftwood Park | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2551 | Bayside Community Center | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2560 | Willowmere Trail | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2562 | Pebble Creek Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2570 | Saltmarsh Master Plan | Project total | Active | 2026-10-26 | 2027-03-12 |  | 128000 | [7 empty] | 1264 | 832 | 432 | 376 | 0 | 0 | 312 | 576 | 241400 | -113400 | 188.6% |  | 3 to fix | Project | 0
2570 | Saltmarsh Master Plan | Phase 3- Choices | Active | 2026-10-26 | 2026-12-06 | 6 | 15500 | 4 | 4 |  |  | 8 |  | 8 | 144 | 144 | 0 | 48 | 0 | 0 | 48 | 48 | 28800 | -13300 | 185.8% | 100% | OK | Phase | 6
2570 | Saltmarsh Master Plan | Phase 4- Final Master Plan | Active | 2026-12-06 | 2027-01-30 | 8 | 47000 | 8 | 16 |  |  | 8 |  | 16 | 384 | 280 | 104 | 192 | 0 | 0 | 64 | 128 | 84160 | -37160 | 179.1% | 100% | Map hours on Timeline | Phase | 8
2570 | Saltmarsh Master Plan | Phase 5- Execution Plan | Active | 2027-02-13 | 2027-03-12 | 4 | 6000 | 4 | 0 |  |  | 10 |  | 0 | 56 | 136 | -80 | 16 | 0 | 0 | 40 | 0 | 11640 | -5640 | 194% | 100% | Over-mapped on Timeline | Phase | 4
2570 | Saltmarsh Master Plan | ASR 1 | Active | 2026-10-26 | 2027-01-03 | 10 | 59500 | 8 | 4 |  |  | 16 |  | 40 | 680 | 272 | 408 | 120 | 0 | 0 | 160 | 400 | 116800 | -57300 | 196.3% | 100% | Map hours on Timeline | Phase | 10
2576 | Westbury Elementary School | Project total | Inactive |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2576 | Westbury Elementary School | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 to fix | Project | 0
2577 | Riverbend Master Plan | CA | Active | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | Enter dates | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2577 | Riverbend Master Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2582 | Bayside Lofts | Project total | Active | 2026-02-01 | 2026-04-25 |  | 23000 | [7 empty] | 72 | 0 | 72 | 12 | 60 | 0 | 0 | 0 | 18480 | 4520 | 80.35% |  | 1 to fix | Project | 0
2582 | Bayside Lofts | CA | Active | 2026-02-01 | 2026-04-25 | 12 | 23000 | 1 |  | 5 |  |  |  |  | 72 | 0 | 72 | 12 | 60 | 0 | 0 | 0 | 18480 | 4520 | 80.35% | 100% | Map hours on Timeline | Phase | 12
2583 | Cypress Point Campus Plan | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2583 | Cypress Point Campus Plan | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2584 | Hollis Campus Plan | Project total | Active | 2026-10-05 | 2026-11-13 |  | 111500 | [7 empty] | 144 | 144 | 0 | 48 | 0 | 96 | 0 | 0 | 33120 | 78380 | 29.7% |  | 5 to fix | Project | 0
2584 | Hollis Campus Plan | Entitlement | Active | 2026-10-05 | 2026-11-13 | 6 | 22500 | 8 |  |  | 16 |  |  |  | 144 | 144 | 0 | 48 | 0 | 96 | 0 | 0 | 33120 | -10620 | 147.2% | 100% | OK | Phase | 6
2584 | Hollis Campus Plan | SD | Active |  |  |  | 15000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0% | 100% | Enter dates | Phase | 0
2584 | Hollis Campus Plan | DD | Active |  |  |  | 26000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000 | 0% | 100% | Enter dates | Phase | 0
2584 | Hollis Campus Plan | CD | Active |  |  |  | 29500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0% | 100% | Enter dates | Phase | 0
2584 | Hollis Campus Plan | Bidding | Active |  |  |  | 3500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0% | 100% | Enter dates | Phase | 0
2584 | Hollis Campus Plan | CA | Active |  |  |  | 15000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0% | 100% | Enter dates | Phase | 0
2622 | Hawthorne Glen Senior Housing | Project total | Active | 2026-10-05 | 2027-10-31 |  | 247500 | [7 empty] | 970 | 885 | 85 | 210 | 288 | 0 | 328 | 144 | 209740 | 37760 | 84.74% |  | 2 to fix | Project | 0
2622 | Hawthorne Glen Senior Housing | DD | Active | 2026-10-05 | 2026-11-02 | 5 | 58500 | 8 | 8 | 16 |  |  | 24 | 8 | 320 | 320 | 0 | 80 | 80 | 0 | 120 | 40 | 69600 | -11100 | 119% | 100% | OK | Phase | 5
2622 | Hawthorne Glen Senior Housing | CD | Active | 2026-11-02 | 2027-10-31 | 52 | 111500 | 1 | 1.5 | 4 |  |  | 4 | 2 | 650 | 565 | 85 | 130 | 208 | 0 | 208 | 104 | 140140 | -28640 | 125.7% | 100% | Map hours on Timeline | Phase | 52
2622 | Hawthorne Glen Senior Housing | CA | Active |  |  |  | 77500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77500 | 0% | 100% | Enter dates | Phase | 0
2626 | Northgate Courtyard | Project total | Active |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2626 | Northgate Courtyard | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
2627 | Ridgeview Lofts | Project total | Active | 2026-10-05 | 2027-01-14 |  | 98500 | [7 empty] | 127.5 | 118 | 9.5 | 52.5 | 30 | 0 | 0 | 45 | 28800 | 69700 | 29.24% |  | 4 to fix | Project | 0
2627 | Ridgeview Lofts | DD | Active | 2026-10-05 | 2027-01-14 | 15 | 30000 | 1.5 | 2 | 2 |  |  |  | 3 | 127.5 | 118 | 9.5 | 52.5 | 30 | 0 | 0 | 45 | 28800 | 1200 | 96% | 100% | Map hours on Timeline | Phase | 15
2627 | Ridgeview Lofts | CD | Active |  |  |  | 43500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 0% | 100% | Enter dates | Phase | 0
2627 | Ridgeview Lofts | Bidding | Active |  |  |  | 5500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0% | 100% | Enter dates | Phase | 0
2627 | Ridgeview Lofts | CA | Active |  |  |  | 19500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19500 | 0% | 100% | Enter dates | Phase | 0
2630 | Birch Roof Deck | Project total | Inactive |  |  |  | 127500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127500 | 0% |  | 5 to fix | Project | 0
2630 | Birch Roof Deck | Entitlement | Inactive |  |  |  | 22000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0% | 0% | Enter dates | Phase | 0
2630 | Birch Roof Deck | SD | Inactive |  |  |  | 26500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 0% | 0% | Enter dates | Phase | 0
2630 | Birch Roof Deck | DD | Inactive |  |  |  | 30500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30500 | 0% | 0% | Enter dates | Phase | 0
2630 | Birch Roof Deck | CD | Inactive |  |  |  | 44000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 0% | 0% | Enter dates | Phase | 0
2630 | Birch Roof Deck | CA | Inactive |  |  |  | 4500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0% | 0% | Enter dates | Phase | 0
2636 | Stonebridge Streetscape | Project total | Active | 2026-10-05 | 2026-11-23 |  | 127500 | [7 empty] | 317 | 40 | 277 | 52 | 36 | 36 | 193 | 0 | 65055 | 62445 | 51.02% |  | 2 to fix | Project | 0
2636 | Stonebridge Streetscape | DD | Active | 2026-10-05 | 2026-10-26 | 4 | 56000 | 8 |  | 4 | 4 | 1 | 16 |  | 132 | 32 | 100 | 32 | 16 | 16 | 68 | 0 | 28380 | 27620 | 50.68% | 100% | Map hours on Timeline | Phase | 4
2636 | Stonebridge Streetscape | CD | Active | 2026-10-26 | 2026-11-23 | 5 | 71500 | 4 |  | 4 | 4 | 1 | 24 |  | 185 | 8 | 177 | 20 | 20 | 20 | 125 | 0 | 36675 | 34825 | 51.29% | 100% | Map hours on Timeline | Phase | 5
2642 | Saltmarsh Terrace | Project total | Active |  |  |  | 404500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404500 | 0% |  | 7 to fix | Project | 0
2642 | Saltmarsh Terrace | Concept | Active |  |  |  | 30500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30500 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | Entitlement | Active |  |  |  | 46000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | SD | Active |  |  |  | 68500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68500 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | DD | Active |  |  |  | 84000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | CD | Active |  |  |  | 99000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | Permitting | Active |  |  |  | 21500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21500 | 0% | 100% | Enter dates | Phase | 0
2642 | Saltmarsh Terrace | CA | Active |  |  |  | 55000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0% | 100% | Enter dates | Phase | 0
2672 | Marigold Plaza | Project total | Active | 2026-10-05 | 2030-01-01 |  | 1117500 | [7 empty] | 1483 | 1544 | -61 | 420 | 120 | 333 | 0 | 610 | 300750 | 816750 | 26.91% |  | 4 to fix | Project | 0
2672 | Marigold Plaza | SD | Active | 2026-10-05 | 2026-11-22 | 7 | 130000 | 10 | 10 |  | 19 |  |  | 30 | 483 | 602 | -119 | 140 | 0 | 133 | 0 | 210 | 95550 | 34450 | 73.5% | 100% | Over-mapped on Timeline | Phase | 7
2672 | Marigold Plaza | DD | Active | 2026-11-22 | 2027-01-30 | 10 | 275500 | 8 | 20 | 12 | 20 |  |  | 40 | 1000 | 942 | 58 | 280 | 120 | 200 | 0 | 400 | 205200 | 70300 | 74.48% | 100% | Map hours on Timeline | Phase | 10
2672 | Marigold Plaza | CD | Active | 2027-03-13 | 2027-12-17 | 40 | 566500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566500 | 0% | 100% | Enter staff hours | Phase | 40
2672 | Marigold Plaza | CA | Active | 2027-12-17 | 2030-01-01 | 107 | 145500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145500 | 0% | 100% | Enter staff hours | Phase | 107
2673 | Meadow Townhomes | Project total | Active | 2026-10-05 | 2028-09-02 |  | 125500 | [7 empty] | 572 | 185 | 387 | 61 | 107 | 44 | 360 | 0 | 116240 | 9260 | 92.62% |  | 6 to fix | Project | 0
2673 | Meadow Townhomes | SD | Active | 2026-10-05 | 2026-11-01 | 4 | 26000 | 8 |  |  | 11 | 1 | 16 |  | 144 | 148 | -4 | 32 | 0 | 44 | 68 | 0 | 29980 | -3980 | 115.3% | 100% | Over-mapped on Timeline | Phase | 4
2673 | Meadow Townhomes | DD | Active | 2026-11-01 | 2027-01-09 | 10 | 26000 | 2 |  | 3.5 |  |  | 10 |  | 155 | 37 | 118 | 20 | 35 | 0 | 100 | 0 | 32050 | -6050 | 123.3% | 100% | Map hours on Timeline | Phase | 10
2673 | Meadow Townhomes | CD | Active | 2027-01-03 | 2027-03-27 | 12 | 41500 | 0.75 |  | 6 |  |  | 16 |  | 273 | 0 | 273 | 9 | 72 | 0 | 192 | 0 | 54210 | -12710 | 130.6% | 100% | Map hours on Timeline | Phase | 12
2673 | Meadow Townhomes | Bidding | Active | 2027-03-21 | 2027-05-15 | 8 | 5500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0% | 100% | Enter staff hours | Phase | 8
2673 | Meadow Townhomes | Permitting | Active | 2027-01-03 | 2027-06-19 | 24 | 5500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0% | 100% | Enter staff hours | Phase | 24
2673 | Meadow Townhomes | CA | Active | 2027-06-13 | 2028-09-02 | 64 | 21000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | 0% | 100% | Enter staff hours | Phase | 64
|  | Project total |  |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
|  | Project total |  |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
|  | Project total |  |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
|  | Project total |  |  |  |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | No phases yet | Project | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  | Phase | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0
[21 empty] | 0 |  | 0

## Timeline
Multi-Phase Timeline
Scenario: Active + Prospective ¦ Rows appear automatically for each staff member with hours on Projects. Type hours into the weeks they work; Placed turns red if it exceeds the Pool.
[7 empty] | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27
Week # | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Week Beginning (Mon) | time axis 2026-10-05 to 2027-09-27
Horizon | [6 empty] | Near | Near | Near | Near | Near | Near | Near | Near | Near | Near | Near | Near | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Mid | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long | Long
STAFFING HEAT MAP — utilization by level (demand ÷ capacity, from Forecast) | [5 empty] | Peak
Principal | [5 empty] | 158.3% | 136.7% | 143.3% | 131.7% | 158.3% | 131.7% | 105% | 91.67% | 91.67% | 90% | 63.33% | 63.33% | 56.67% | 56.67% | 56.67% | 56.67% | 40% | 46.67% | 26.67% | 40% | 46.67% | 53.33% | 53.33% | 46.67% | 0% | 0% | 0% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Director | [5 empty] | 118.8% | 56.25% | 81.25% | 81.25% | 81.25% | 81.25% | 81.25% | 81.25% | 118.8% | 118.8% | 71.88% | 71.88% | 46.88% | 46.88% | 46.88% | 93.75% | 87.5% | 112.5% | 75% | 28.12% | 28.12% | 28.12% | 28.12% | 28.12% | 15.62% | 3.125% | 3.125% | 15.62% | 15.62% | 15.62% | 15.62% | 62.5% | 62.5% | 62.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 6.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Senior Designer | [5 empty] | 144.4% | 144.4% | 144.4% | 144.4% | 144.4% | 111.1% | 111.1% | 66.67% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Mid Level Designer | [5 empty] | 90.28% | 56.94% | 79.17% | 79.17% | 90.28% | 66.67% | 61.11% | 66.67% | 66.67% | 66.67% | 50% | 50% | 22.22% | 22.22% | 22.22% | 44.44% | 44.44% | 44.44% | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.78% | 27.78% | 27.78% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Project Designer | [5 empty] | 166.7% | 105.6% | 105.6% | 127.8% | 127.8% | 105.6% | 105.6% | 105.6% | 155.6% | 155.6% | 111.1% | 111.1% | 122.2% | 111.1% | 111.1% | 133.3% | 166.7% | 166.7% | 55.56% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Firm Total | [5 empty] | 120.3% | 97.88% | 109.7% | 110.2% | 120.3% | 97.88% | 89.41% | 80.93% | 90.25% | 89.83% | 64.83% | 64.83% | 52.97% | 51.27% | 51.27% | 67.8% | 67.8% | 72.88% | 32.2% | 13.98% | 15.68% | 17.37% | 17.37% | 15.68% | 2.119% | 0.4237% | 0.4237% | 2.966% | 2.966% | 2.966% | 2.966% | 19.49% | 17.8% | 17.8% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 0.8475% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
# Levels understaffed | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase colors: | [6 empty] | 2026-10-05: Concept; 2026-11-02: Entitlement; 2026-11-30: SD; 2026-12-28: DD; 2027-01-25: CD; 2027-02-22: Bidding; 2027-03-22: Permitting; 2027-04-19: CA; 2027-05-17: Other/custom
MAP HOURS TO WEEKS — every staff member is listed under each project. Click the +/- beside a project to collapse or expand its staff. Rows with hours on Projects show a Pool; greyed rows have none. Type hours into the weeks they work; Placed turns red if it exceeds the Pool.
Project No. | Project Name | Status | Staff | Pool Hrs | Placed Hrs | Left | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | Project row | Level | Start | End | Weight | Slot | Projects not yet listed
| 2256 · Marigold Promenade | Active |  | 81 | 80 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2256 | Marigold Promenade | Active | PK | 27 | 26 | 1 | 2027-04-05: 2; 2027-04-12: 2; 2027-04-19: 2; 2027-04-26: 2; 2027-05-03: 2; 2027-05-10: 2; 2027-05-17: 2; 2027-05-24: 2; 2027-05-31: 2; 2027-06-07: 2; 2027-06-14: 2; 2027-06-21: 2; 2027-06-28: 2 | 1 | Principal | 2027-04-01 | 2027-10-05 | 1 | 1
2256 | Marigold Promenade | Active | DF | 0 | 0 | 0 | [52 empty] | 1 | Principal | 2027-04-01 | 2027-10-05 | 1 | 2
2256 | Marigold Promenade | Active | KJ | 54 | 54 | 0 | 2027-04-05: 4; 2027-04-12: 4; 2027-04-19: 4; 2027-04-26: 4; 2027-05-03: 4; 2027-05-10: 4; 2027-05-17: 4; 2027-05-24: 4; 2027-05-31: 4; 2027-06-07: 4; 2027-06-14: 4; 2027-06-21: 4; 2027-06-28: 4; 2027-07-05: 2 | 1 | Director | 2027-04-01 | 2027-10-05 | 1 | 3
2256 | Marigold Promenade | Active | HL | 0 | 0 | 0 | [52 empty] | 1 | Senior Designer | 2027-04-01 | 2027-10-05 | 1 | 4
2256 | Marigold Promenade | Active | EHH | 0 | 0 | 0 | [52 empty] | 1 | Mid Level Designer | 2027-04-01 | 2027-10-05 | 1 | 5
2256 | Marigold Promenade | Active | KD | 0 | 0 | 0 | [52 empty] | 1 | Mid Level Designer | 2027-04-01 | 2027-10-05 | 1 | 6
2256 | Marigold Promenade | Active | XX | 0 | 0 | 0 | [52 empty] | 1 | Project Designer | 2027-04-01 | 2027-10-05 | 1 | 7
2256 | Marigold Promenade | Active |  |  | 0 | [53 empty] | 1 |  | 2027-04-01 | 2027-10-05 | 1 | 8
| 2348 · Fairhaven Senior Housing | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2348 | Fairhaven Senior Housing | Inactive | PK | 0 | 0 | 0 | [52 empty] | 3 | Principal |  |  | 0 | 1
2348 | Fairhaven Senior Housing | Inactive | DF | 0 | 0 | 0 | [52 empty] | 3 | Principal |  |  | 0 | 2
2348 | Fairhaven Senior Housing | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 3 | Director |  |  | 0 | 3
2348 | Fairhaven Senior Housing | Inactive | HL | 0 | 0 | 0 | [52 empty] | 3 | Senior Designer |  |  | 0 | 4
2348 | Fairhaven Senior Housing | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 3 | Mid Level Designer |  |  | 0 | 5
2348 | Fairhaven Senior Housing | Inactive | KD | 0 | 0 | 0 | [52 empty] | 3 | Mid Level Designer |  |  | 0 | 6
2348 | Fairhaven Senior Housing | Inactive | XX | 0 | 0 | 0 | [52 empty] | 3 | Project Designer |  |  | 0 | 7
2348 | Fairhaven Senior Housing | Inactive |  |  | 0 | [53 empty] | 3 |  |  |  | 0 | 8
| 2370 · Tamarack Housing | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2370 | Tamarack Housing | Inactive | PK | 0 | 0 | 0 | [52 empty] | 12 | Principal |  |  | 0 | 1
2370 | Tamarack Housing | Inactive | DF | 0 | 0 | 0 | [52 empty] | 12 | Principal |  |  | 0 | 2
2370 | Tamarack Housing | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 12 | Director |  |  | 0 | 3
2370 | Tamarack Housing | Inactive | HL | 0 | 0 | 0 | [52 empty] | 12 | Senior Designer |  |  | 0 | 4
2370 | Tamarack Housing | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 12 | Mid Level Designer |  |  | 0 | 5
2370 | Tamarack Housing | Inactive | KD | 0 | 0 | 0 | [52 empty] | 12 | Mid Level Designer |  |  | 0 | 6
2370 | Tamarack Housing | Inactive | XX | 0 | 0 | 0 | [52 empty] | 12 | Project Designer |  |  | 0 | 7
2370 | Tamarack Housing | Inactive |  |  | 0 | [53 empty] | 12 |  |  |  | 0 | 8
| 2458 · Summit Ridge Village | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2458 | Summit Ridge Village | Inactive | PK | 0 | 0 | 0 | [52 empty] | 21 | Principal |  |  | 0 | 1
2458 | Summit Ridge Village | Inactive | DF | 0 | 0 | 0 | [52 empty] | 21 | Principal |  |  | 0 | 2
2458 | Summit Ridge Village | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 21 | Director |  |  | 0 | 3
2458 | Summit Ridge Village | Inactive | HL | 0 | 0 | 0 | [52 empty] | 21 | Senior Designer |  |  | 0 | 4
2458 | Summit Ridge Village | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 21 | Mid Level Designer |  |  | 0 | 5
2458 | Summit Ridge Village | Inactive | KD | 0 | 0 | 0 | [52 empty] | 21 | Mid Level Designer |  |  | 0 | 6
2458 | Summit Ridge Village | Inactive | XX | 0 | 0 | 0 | [52 empty] | 21 | Project Designer |  |  | 0 | 7
2458 | Summit Ridge Village | Inactive |  |  | 0 | [53 empty] | 21 |  |  |  | 0 | 8
| 2469 · Fairhaven Village | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2469 | Fairhaven Village | Active | PK | 0 | 0 | 0 | [52 empty] | 30 | Principal |  |  | 1 | 1
2469 | Fairhaven Village | Active | DF | 0 | 0 | 0 | [52 empty] | 30 | Principal |  |  | 1 | 2
2469 | Fairhaven Village | Active | KJ | 0 | 0 | 0 | [52 empty] | 30 | Director |  |  | 1 | 3
2469 | Fairhaven Village | Active | HL | 0 | 0 | 0 | [52 empty] | 30 | Senior Designer |  |  | 1 | 4
2469 | Fairhaven Village | Active | EHH | 0 | 0 | 0 | [52 empty] | 30 | Mid Level Designer |  |  | 1 | 5
2469 | Fairhaven Village | Active | KD | 0 | 0 | 0 | [52 empty] | 30 | Mid Level Designer |  |  | 1 | 6
2469 | Fairhaven Village | Active | XX | 0 | 0 | 0 | [52 empty] | 30 | Project Designer |  |  | 1 | 7
2469 | Fairhaven Village | Active |  |  | 0 | [53 empty] | 30 |  |  |  | 1 | 8
| 2470 · Canyon Vista Park | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2470 | Canyon Vista Park | Active | PK | 0 | 0 | 0 | [52 empty] | 39 | Principal |  |  | 1 | 1
2470 | Canyon Vista Park | Active | DF | 0 | 0 | 0 | [52 empty] | 39 | Principal |  |  | 1 | 2
2470 | Canyon Vista Park | Active | KJ | 0 | 0 | 0 | [52 empty] | 39 | Director |  |  | 1 | 3
2470 | Canyon Vista Park | Active | HL | 0 | 0 | 0 | [52 empty] | 39 | Senior Designer |  |  | 1 | 4
2470 | Canyon Vista Park | Active | EHH | 0 | 0 | 0 | [52 empty] | 39 | Mid Level Designer |  |  | 1 | 5
2470 | Canyon Vista Park | Active | KD | 0 | 0 | 0 | [52 empty] | 39 | Mid Level Designer |  |  | 1 | 6
2470 | Canyon Vista Park | Active | XX | 0 | 0 | 0 | [52 empty] | 39 | Project Designer |  |  | 1 | 7
2470 | Canyon Vista Park | Active |  |  | 0 | [53 empty] | 39 |  |  |  | 1 | 8
| 2489 · Harbor Mobility Hub | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2489 | Harbor Mobility Hub | Active | PK | 0 | 0 | 0 | [52 empty] | 48 | Principal |  |  | 1 | 1
2489 | Harbor Mobility Hub | Active | DF | 0 | 0 | 0 | [52 empty] | 48 | Principal |  |  | 1 | 2
2489 | Harbor Mobility Hub | Active | KJ | 0 | 0 | 0 | [52 empty] | 48 | Director |  |  | 1 | 3
2489 | Harbor Mobility Hub | Active | HL | 0 | 0 | 0 | [52 empty] | 48 | Senior Designer |  |  | 1 | 4
2489 | Harbor Mobility Hub | Active | EHH | 0 | 0 | 0 | [52 empty] | 48 | Mid Level Designer |  |  | 1 | 5
2489 | Harbor Mobility Hub | Active | KD | 0 | 0 | 0 | [52 empty] | 48 | Mid Level Designer |  |  | 1 | 6
2489 | Harbor Mobility Hub | Active | XX | 0 | 0 | 0 | [52 empty] | 48 | Project Designer |  |  | 1 | 7
2489 | Harbor Mobility Hub | Active |  |  | 0 | [53 empty] | 48 |  |  |  | 1 | 8
| 2494 · Laurel Park Garden | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2494 | Laurel Park Garden | Active | PK | 0 | 0 | 0 | [52 empty] | 57 | Principal |  |  | 1 | 1
2494 | Laurel Park Garden | Active | DF | 0 | 0 | 0 | [52 empty] | 57 | Principal |  |  | 1 | 2
2494 | Laurel Park Garden | Active | KJ | 0 | 0 | 0 | [52 empty] | 57 | Director |  |  | 1 | 3
2494 | Laurel Park Garden | Active | HL | 0 | 0 | 0 | [52 empty] | 57 | Senior Designer |  |  | 1 | 4
2494 | Laurel Park Garden | Active | EHH | 0 | 0 | 0 | [52 empty] | 57 | Mid Level Designer |  |  | 1 | 5
2494 | Laurel Park Garden | Active | KD | 0 | 0 | 0 | [52 empty] | 57 | Mid Level Designer |  |  | 1 | 6
2494 | Laurel Park Garden | Active | XX | 0 | 0 | 0 | [52 empty] | 57 | Project Designer |  |  | 1 | 7
2494 | Laurel Park Garden | Active |  |  | 0 | [53 empty] | 57 |  |  |  | 1 | 8
| 2499 · Zephyr Creative Office | Active |  | 300 | 300 | 0 | 0 | 28 | 28 | 28 | 28 | 28 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2499 | Zephyr Creative Office | Active | PK | 40 | 40 | 0 | 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 4; 2026-12-07: 4; 2026-12-14: 4 | 61 | Principal | 2026-10-12 | 2026-12-20 | 1 | 1
2499 | Zephyr Creative Office | Active | DF | 0 | 0 | 0 | [52 empty] | 61 | Principal | 2026-10-12 | 2026-12-20 | 1 | 2
2499 | Zephyr Creative Office | Active | KJ | 80 | 80 | 0 | 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8 | 61 | Director | 2026-10-12 | 2026-12-20 | 1 | 3
2499 | Zephyr Creative Office | Active | HL | 0 | 0 | 0 | [52 empty] | 61 | Senior Designer | 2026-10-12 | 2026-12-20 | 1 | 4
2499 | Zephyr Creative Office | Active | EHH | 0 | 0 | 0 | [52 empty] | 61 | Mid Level Designer | 2026-10-12 | 2026-12-20 | 1 | 5
2499 | Zephyr Creative Office | Active | KD | 180 | 180 | 0 | 2026-10-12: 16; 2026-10-19: 16; 2026-10-26: 16; 2026-11-02: 16; 2026-11-09: 16; 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 20 | 61 | Mid Level Designer | 2026-10-12 | 2026-12-20 | 1 | 6
2499 | Zephyr Creative Office | Active | XX | 0 | 0 | 0 | [52 empty] | 61 | Project Designer | 2026-10-12 | 2026-12-20 | 1 | 7
2499 | Zephyr Creative Office | Active |  |  | 0 | [53 empty] | 61 |  | 2026-10-12 | 2026-12-20 | 1 | 8
| 2545 · Mariner Courtyard | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2545 | Mariner Courtyard | Inactive | PK | 0 | 0 | 0 | [52 empty] | 63 | Principal |  |  | 0 | 1
2545 | Mariner Courtyard | Inactive | DF | 0 | 0 | 0 | [52 empty] | 63 | Principal |  |  | 0 | 2
2545 | Mariner Courtyard | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 63 | Director |  |  | 0 | 3
2545 | Mariner Courtyard | Inactive | HL | 0 | 0 | 0 | [52 empty] | 63 | Senior Designer |  |  | 0 | 4
2545 | Mariner Courtyard | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 63 | Mid Level Designer |  |  | 0 | 5
2545 | Mariner Courtyard | Inactive | KD | 0 | 0 | 0 | [52 empty] | 63 | Mid Level Designer |  |  | 0 | 6
2545 | Mariner Courtyard | Inactive | XX | 0 | 0 | 0 | [52 empty] | 63 | Project Designer |  |  | 0 | 7
2545 | Mariner Courtyard | Inactive |  |  | 0 | [53 empty] | 63 |  |  |  | 0 | 8
| 2550 · Driftwood Park | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2550 | Driftwood Park | Active | PK | 0 | 0 | 0 | [52 empty] | 72 | Principal |  |  | 1 | 1
2550 | Driftwood Park | Active | DF | 0 | 0 | 0 | [52 empty] | 72 | Principal |  |  | 1 | 2
2550 | Driftwood Park | Active | KJ | 0 | 0 | 0 | [52 empty] | 72 | Director |  |  | 1 | 3
2550 | Driftwood Park | Active | HL | 0 | 0 | 0 | [52 empty] | 72 | Senior Designer |  |  | 1 | 4
2550 | Driftwood Park | Active | EHH | 0 | 0 | 0 | [52 empty] | 72 | Mid Level Designer |  |  | 1 | 5
2550 | Driftwood Park | Active | KD | 0 | 0 | 0 | [52 empty] | 72 | Mid Level Designer |  |  | 1 | 6
2550 | Driftwood Park | Active | XX | 0 | 0 | 0 | [52 empty] | 72 | Project Designer |  |  | 1 | 7
2550 | Driftwood Park | Active |  |  | 0 | [53 empty] | 72 |  |  |  | 1 | 8
| 2551 · Bayside Community Center | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2551 | Bayside Community Center | Active | PK | 0 | 0 | 0 | [52 empty] | 81 | Principal |  |  | 1 | 1
2551 | Bayside Community Center | Active | DF | 0 | 0 | 0 | [52 empty] | 81 | Principal |  |  | 1 | 2
2551 | Bayside Community Center | Active | KJ | 0 | 0 | 0 | [52 empty] | 81 | Director |  |  | 1 | 3
2551 | Bayside Community Center | Active | HL | 0 | 0 | 0 | [52 empty] | 81 | Senior Designer |  |  | 1 | 4
2551 | Bayside Community Center | Active | EHH | 0 | 0 | 0 | [52 empty] | 81 | Mid Level Designer |  |  | 1 | 5
2551 | Bayside Community Center | Active | KD | 0 | 0 | 0 | [52 empty] | 81 | Mid Level Designer |  |  | 1 | 6
2551 | Bayside Community Center | Active | XX | 0 | 0 | 0 | [52 empty] | 81 | Project Designer |  |  | 1 | 7
2551 | Bayside Community Center | Active |  |  | 0 | [53 empty] | 81 |  |  |  | 1 | 8
| 2560 · Willowmere Trail | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2560 | Willowmere Trail | Active | PK | 0 | 0 | 0 | [52 empty] | 90 | Principal |  |  | 1 | 1
2560 | Willowmere Trail | Active | DF | 0 | 0 | 0 | [52 empty] | 90 | Principal |  |  | 1 | 2
2560 | Willowmere Trail | Active | KJ | 0 | 0 | 0 | [52 empty] | 90 | Director |  |  | 1 | 3
2560 | Willowmere Trail | Active | HL | 0 | 0 | 0 | [52 empty] | 90 | Senior Designer |  |  | 1 | 4
2560 | Willowmere Trail | Active | EHH | 0 | 0 | 0 | [52 empty] | 90 | Mid Level Designer |  |  | 1 | 5
2560 | Willowmere Trail | Active | KD | 0 | 0 | 0 | [52 empty] | 90 | Mid Level Designer |  |  | 1 | 6
2560 | Willowmere Trail | Active | XX | 0 | 0 | 0 | [52 empty] | 90 | Project Designer |  |  | 1 | 7
2560 | Willowmere Trail | Active |  |  | 0 | [53 empty] | 90 |  |  |  | 1 | 8
| 2562 · Pebble Creek Courtyard | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2562 | Pebble Creek Courtyard | Active | PK | 0 | 0 | 0 | [52 empty] | 99 | Principal |  |  | 1 | 1
2562 | Pebble Creek Courtyard | Active | DF | 0 | 0 | 0 | [52 empty] | 99 | Principal |  |  | 1 | 2
2562 | Pebble Creek Courtyard | Active | KJ | 0 | 0 | 0 | [52 empty] | 99 | Director |  |  | 1 | 3
2562 | Pebble Creek Courtyard | Active | HL | 0 | 0 | 0 | [52 empty] | 99 | Senior Designer |  |  | 1 | 4
2562 | Pebble Creek Courtyard | Active | EHH | 0 | 0 | 0 | [52 empty] | 99 | Mid Level Designer |  |  | 1 | 5
2562 | Pebble Creek Courtyard | Active | KD | 0 | 0 | 0 | [52 empty] | 99 | Mid Level Designer |  |  | 1 | 6
2562 | Pebble Creek Courtyard | Active | XX | 0 | 0 | 0 | [52 empty] | 99 | Project Designer |  |  | 1 | 7
2562 | Pebble Creek Courtyard | Active |  |  | 0 | [53 empty] | 99 |  |  |  | 1 | 8
| 2570 · Saltmarsh Master Plan | Active |  | 1264 | 552 | 712 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 24 | 24 | 32 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2570 | Saltmarsh Master Plan | Active | PK | 184 | 184 | 0 | 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 16; 2027-03-01: 16; 2027-03-08: 16 | 108 | Principal | 2026-10-26 | 2027-03-12 | 1 | 1
2570 | Saltmarsh Master Plan | Active | DF | 192 | 192 | 0 | 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 16; 2027-02-15: 16; 2027-02-22: 16; 2027-03-01: 16; 2027-03-08: 8 | 108 | Principal | 2026-10-26 | 2027-03-12 | 1 | 2
2570 | Saltmarsh Master Plan | Active | KJ | 0 | 0 | 0 | [52 empty] | 108 | Director | 2026-10-26 | 2027-03-12 | 1 | 3
2570 | Saltmarsh Master Plan | Active | HL | 0 | 0 | 0 | [52 empty] | 108 | Senior Designer | 2026-10-26 | 2027-03-12 | 1 | 4
2570 | Saltmarsh Master Plan | Active | EHH | 312 | 176 | 136 | 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 16; 2026-12-14: 16; 2026-12-21: 16; 2026-12-28: 16; 2027-01-04: 16; 2027-01-11: 16; 2027-01-18: 16; 2027-01-25: 16 | 108 | Mid Level Designer | 2026-10-26 | 2027-03-12 | 1 | 5
2570 | Saltmarsh Master Plan | Active | KD | 0 | 0 | 0 | [52 empty] | 108 | Mid Level Designer | 2026-10-26 | 2027-03-12 | 1 | 6
2570 | Saltmarsh Master Plan | Active | XX | 576 | 0 | 576 | [52 empty] | 108 | Project Designer | 2026-10-26 | 2027-03-12 | 1 | 7
2570 | Saltmarsh Master Plan | Active |  |  | 0 | [53 empty] | 108 |  | 2026-10-26 | 2027-03-12 | 1 | 8
| 2576 · Westbury Elementary School | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2576 | Westbury Elementary School | Inactive | PK | 0 | 0 | 0 | [52 empty] | 113 | Principal |  |  | 0 | 1
2576 | Westbury Elementary School | Inactive | DF | 0 | 0 | 0 | [52 empty] | 113 | Principal |  |  | 0 | 2
2576 | Westbury Elementary School | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 113 | Director |  |  | 0 | 3
2576 | Westbury Elementary School | Inactive | HL | 0 | 0 | 0 | [52 empty] | 113 | Senior Designer |  |  | 0 | 4
2576 | Westbury Elementary School | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 113 | Mid Level Designer |  |  | 0 | 5
2576 | Westbury Elementary School | Inactive | KD | 0 | 0 | 0 | [52 empty] | 113 | Mid Level Designer |  |  | 0 | 6
2576 | Westbury Elementary School | Inactive | XX | 0 | 0 | 0 | [52 empty] | 113 | Project Designer |  |  | 0 | 7
2576 | Westbury Elementary School | Inactive |  |  | 0 | [53 empty] | 113 |  |  |  | 0 | 8
| 2577 · Riverbend Master Plan | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2577 | Riverbend Master Plan | Active | PK | 0 | 0 | 0 | [52 empty] | 122 | Principal |  |  | 1 | 1
2577 | Riverbend Master Plan | Active | DF | 0 | 0 | 0 | [52 empty] | 122 | Principal |  |  | 1 | 2
2577 | Riverbend Master Plan | Active | KJ | 0 | 0 | 0 | [52 empty] | 122 | Director |  |  | 1 | 3
2577 | Riverbend Master Plan | Active | HL | 0 | 0 | 0 | [52 empty] | 122 | Senior Designer |  |  | 1 | 4
2577 | Riverbend Master Plan | Active | EHH | 0 | 0 | 0 | [52 empty] | 122 | Mid Level Designer |  |  | 1 | 5
2577 | Riverbend Master Plan | Active | KD | 0 | 0 | 0 | [52 empty] | 122 | Mid Level Designer |  |  | 1 | 6
2577 | Riverbend Master Plan | Active | XX | 0 | 0 | 0 | [52 empty] | 122 | Project Designer |  |  | 1 | 7
2577 | Riverbend Master Plan | Active |  |  | 0 | [53 empty] | 122 |  |  |  | 1 | 8
| 2582 · Bayside Lofts | Active |  | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 8 | 12 | 8 | 8 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2582 | Bayside Lofts | Active | PK | 12 | 12 | 0 | 2027-01-25: 4; 2027-02-15: 4; 2027-03-08: 4 | 131 | Principal | 2026-02-01 | 2026-04-25 | 1 | 1
2582 | Bayside Lofts | Active | DF | 0 | 0 | 0 | [52 empty] | 131 | Principal | 2026-02-01 | 2026-04-25 | 1 | 2
2582 | Bayside Lofts | Active | KJ | 60 | 60 | 0 | 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 8; 2027-03-08: 8; 2027-03-15: 4 | 131 | Director | 2026-02-01 | 2026-04-25 | 1 | 3
2582 | Bayside Lofts | Active | HL | 0 | 0 | 0 | [52 empty] | 131 | Senior Designer | 2026-02-01 | 2026-04-25 | 1 | 4
2582 | Bayside Lofts | Active | EHH | 0 | 0 | 0 | [52 empty] | 131 | Mid Level Designer | 2026-02-01 | 2026-04-25 | 1 | 5
2582 | Bayside Lofts | Active | KD | 0 | 0 | 0 | [52 empty] | 131 | Mid Level Designer | 2026-02-01 | 2026-04-25 | 1 | 6
2582 | Bayside Lofts | Active | XX | 0 | 0 | 0 | [52 empty] | 131 | Project Designer | 2026-02-01 | 2026-04-25 | 1 | 7
2582 | Bayside Lofts | Active |  |  | 0 | [53 empty] | 131 |  | 2026-02-01 | 2026-04-25 | 1 | 8
| 2583 · Cypress Point Campus Plan | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2583 | Cypress Point Campus Plan | Active | PK | 0 | 0 | 0 | [52 empty] | 133 | Principal |  |  | 1 | 1
2583 | Cypress Point Campus Plan | Active | DF | 0 | 0 | 0 | [52 empty] | 133 | Principal |  |  | 1 | 2
2583 | Cypress Point Campus Plan | Active | KJ | 0 | 0 | 0 | [52 empty] | 133 | Director |  |  | 1 | 3
2583 | Cypress Point Campus Plan | Active | HL | 0 | 0 | 0 | [52 empty] | 133 | Senior Designer |  |  | 1 | 4
2583 | Cypress Point Campus Plan | Active | EHH | 0 | 0 | 0 | [52 empty] | 133 | Mid Level Designer |  |  | 1 | 5
2583 | Cypress Point Campus Plan | Active | KD | 0 | 0 | 0 | [52 empty] | 133 | Mid Level Designer |  |  | 1 | 6
2583 | Cypress Point Campus Plan | Active | XX | 0 | 0 | 0 | [52 empty] | 133 | Project Designer |  |  | 1 | 7
2583 | Cypress Point Campus Plan | Active |  |  | 0 | [53 empty] | 133 |  |  |  | 1 | 8
| 2584 · Hollis Campus Plan | Active |  | 144 | 144 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2584 | Hollis Campus Plan | Active | PK | 48 | 48 | 0 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8 | 142 | Principal | 2026-10-05 | 2026-11-13 | 1 | 1
2584 | Hollis Campus Plan | Active | DF | 0 | 0 | 0 | [52 empty] | 142 | Principal | 2026-10-05 | 2026-11-13 | 1 | 2
2584 | Hollis Campus Plan | Active | KJ | 0 | 0 | 0 | [52 empty] | 142 | Director | 2026-10-05 | 2026-11-13 | 1 | 3
2584 | Hollis Campus Plan | Active | HL | 96 | 96 | 0 | 2026-10-05: 16; 2026-10-12: 16; 2026-10-19: 16; 2026-10-26: 16; 2026-11-02: 16; 2026-11-09: 16 | 142 | Senior Designer | 2026-10-05 | 2026-11-13 | 1 | 4
2584 | Hollis Campus Plan | Active | EHH | 0 | 0 | 0 | [52 empty] | 142 | Mid Level Designer | 2026-10-05 | 2026-11-13 | 1 | 5
2584 | Hollis Campus Plan | Active | KD | 0 | 0 | 0 | [52 empty] | 142 | Mid Level Designer | 2026-10-05 | 2026-11-13 | 1 | 6
2584 | Hollis Campus Plan | Active | XX | 0 | 0 | 0 | [52 empty] | 142 | Project Designer | 2026-10-05 | 2026-11-13 | 1 | 7
2584 | Hollis Campus Plan | Active |  |  | 0 | [53 empty] | 142 |  | 2026-10-05 | 2026-11-13 | 1 | 8
| 2622 · Hawthorne Glen Senior Housing | Active |  | 970 | 821 | 149 | 64 | 64 | 64 | 64 | 64 | 44 | 44 | 44 | 44 | 1 | 1 | 1 | 1 | 1 | 40 | 52 | 52 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 40 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2622 | Hawthorne Glen Senior Housing | Active | PK | 92 | 40 | 52 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8; 2026-11-02: 8 | 149 | Principal | 2026-10-05 | 2027-10-31 | 1 | 1
2622 | Hawthorne Glen Senior Housing | Active | DF | 118 | 40 | 78 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8; 2026-11-02: 8 | 149 | Principal | 2026-10-05 | 2027-10-31 | 1 | 2
2622 | Hawthorne Glen Senior Housing | Active | KJ | 288 | 273 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 1 | 1 | 1 | 1 | 1 | 16 | 16 | 16 | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16 | 16 | 16 | [19 empty] | 149 | Director | 2026-10-05 | 2027-10-31 | 1 | 3
2622 | Hawthorne Glen Senior Housing | Active | HL | 0 | 0 | 0 | [52 empty] | 149 | Senior Designer | 2026-10-05 | 2027-10-31 | 1 | 4
2622 | Hawthorne Glen Senior Housing | Active | EHH | 0 | 0 | 0 | [52 empty] | 149 | Mid Level Designer | 2026-10-05 | 2027-10-31 | 1 | 5
2622 | Hawthorne Glen Senior Housing | Active | KD | 328 | 324 | 4 | 2026-10-05: 24; 2026-10-12: 24; 2026-10-19: 24; 2026-10-26: 24; 2026-11-02: 24; 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 20; 2027-01-11: 16; 2027-01-18: 16; 2027-01-25: 16; 2027-02-01: 16; 2027-05-03: 20; 2027-05-10: 20; 2027-05-17: 20 | 149 | Mid Level Designer | 2026-10-05 | 2027-10-31 | 1 | 6
2622 | Hawthorne Glen Senior Housing | Active | XX | 144 | 144 | 0 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2027-01-11: 8; 2027-01-18: 20; 2027-01-25: 20; 2027-02-01: 20; 2027-05-03: 4 | 149 | Project Designer | 2026-10-05 | 2027-10-31 | 1 | 7
2622 | Hawthorne Glen Senior Housing | Active |  |  | 0 | [53 empty] | 149 |  | 2026-10-05 | 2027-10-31 | 1 | 8
| 2626 · Northgate Courtyard | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2626 | Northgate Courtyard | Active | PK | 0 | 0 | 0 | [52 empty] | 153 | Principal |  |  | 1 | 1
2626 | Northgate Courtyard | Active | DF | 0 | 0 | 0 | [52 empty] | 153 | Principal |  |  | 1 | 2
2626 | Northgate Courtyard | Active | KJ | 0 | 0 | 0 | [52 empty] | 153 | Director |  |  | 1 | 3
2626 | Northgate Courtyard | Active | HL | 0 | 0 | 0 | [52 empty] | 153 | Senior Designer |  |  | 1 | 4
2626 | Northgate Courtyard | Active | EHH | 0 | 0 | 0 | [52 empty] | 153 | Mid Level Designer |  |  | 1 | 5
2626 | Northgate Courtyard | Active | KD | 0 | 0 | 0 | [52 empty] | 153 | Mid Level Designer |  |  | 1 | 6
2626 | Northgate Courtyard | Active | XX | 0 | 0 | 0 | [52 empty] | 153 | Project Designer |  |  | 1 | 7
2626 | Northgate Courtyard | Active |  |  | 0 | [53 empty] | 153 |  |  |  | 1 | 8
| 2627 · Ridgeview Lofts | Active |  | 127.5 | 118 | 9.5 | 12 | 12 | 13 | 13 | 5 | 5 | 5 | 13 | 12 | 4 | 4 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2627 | Ridgeview Lofts | Active | PK | 22.5 | 22 | 0.5 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 1; 2026-10-26: 1; 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 1 | 162 | Principal | 2026-10-05 | 2027-01-14 | 1 | 1
2627 | Ridgeview Lofts | Active | DF | 30 | 30 | 0 | 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 2; 2027-01-11: 2 | 162 | Principal | 2026-10-05 | 2027-01-14 | 1 | 2
2627 | Ridgeview Lofts | Active | KJ | 30 | 30 | 0 | 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 2; 2027-01-11: 2 | 162 | Director | 2026-10-05 | 2027-01-14 | 1 | 3
2627 | Ridgeview Lofts | Active | HL | 0 | 0 | 0 | [52 empty] | 162 | Senior Designer | 2026-10-05 | 2027-01-14 | 1 | 4
2627 | Ridgeview Lofts | Active | EHH | 0 | 0 | 0 | [52 empty] | 162 | Mid Level Designer | 2026-10-05 | 2027-01-14 | 1 | 5
2627 | Ridgeview Lofts | Active | KD | 0 | 0 | 0 | [52 empty] | 162 | Mid Level Designer | 2026-10-05 | 2027-01-14 | 1 | 6
2627 | Ridgeview Lofts | Active | XX | 45 | 36 | 9 | 2026-10-19: 8; 2026-10-26: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-21: 4 | 162 | Project Designer | 2026-10-05 | 2027-01-14 | 1 | 7
2627 | Ridgeview Lofts | Active |  |  | 0 | [53 empty] | 162 |  | 2026-10-05 | 2027-01-14 | 1 | 8
| 2630 · Birch Roof Deck | Inactive |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2630 | Birch Roof Deck | Inactive | PK | 0 | 0 | 0 | [52 empty] | 167 | Principal |  |  | 0 | 1
2630 | Birch Roof Deck | Inactive | DF | 0 | 0 | 0 | [52 empty] | 167 | Principal |  |  | 0 | 2
2630 | Birch Roof Deck | Inactive | KJ | 0 | 0 | 0 | [52 empty] | 167 | Director |  |  | 0 | 3
2630 | Birch Roof Deck | Inactive | HL | 0 | 0 | 0 | [52 empty] | 167 | Senior Designer |  |  | 0 | 4
2630 | Birch Roof Deck | Inactive | EHH | 0 | 0 | 0 | [52 empty] | 167 | Mid Level Designer |  |  | 0 | 5
2630 | Birch Roof Deck | Inactive | KD | 0 | 0 | 0 | [52 empty] | 167 | Mid Level Designer |  |  | 0 | 6
2630 | Birch Roof Deck | Inactive | XX | 0 | 0 | 0 | [52 empty] | 167 | Project Designer |  |  | 0 | 7
2630 | Birch Roof Deck | Inactive |  |  | 0 | [53 empty] | 167 |  |  |  | 0 | 8
| 2636 · Stonebridge Streetscape | Active |  | 317 | 32 | 285 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2636 | Stonebridge Streetscape | Active | PK | 52 | 32 | 20 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8 | 173 | Principal | 2026-10-05 | 2026-11-23 | 1 | 1
2636 | Stonebridge Streetscape | Active | DF | 0 | 0 | 0 | [52 empty] | 173 | Principal | 2026-10-05 | 2026-11-23 | 1 | 2
2636 | Stonebridge Streetscape | Active | KJ | 36 | 0 | 36 | [52 empty] | 173 | Director | 2026-10-05 | 2026-11-23 | 1 | 3
2636 | Stonebridge Streetscape | Active | HL | 36 | 0 | 36 | [52 empty] | 173 | Senior Designer | 2026-10-05 | 2026-11-23 | 1 | 4
2636 | Stonebridge Streetscape | Active | EHH | 9 | 0 | 9 | [52 empty] | 173 | Mid Level Designer | 2026-10-05 | 2026-11-23 | 1 | 5
2636 | Stonebridge Streetscape | Active | KD | 184 | 0 | 184 | [52 empty] | 173 | Mid Level Designer | 2026-10-05 | 2026-11-23 | 1 | 6
2636 | Stonebridge Streetscape | Active | XX | 0 | 0 | 0 | [52 empty] | 173 | Project Designer | 2026-10-05 | 2026-11-23 | 1 | 7
2636 | Stonebridge Streetscape | Active |  |  | 0 | [53 empty] | 173 |  | 2026-10-05 | 2026-11-23 | 1 | 8
| 2642 · Saltmarsh Terrace | Active |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2642 | Saltmarsh Terrace | Active | PK | 0 | 0 | 0 | [52 empty] | 176 | Principal |  |  | 1 | 1
2642 | Saltmarsh Terrace | Active | DF | 0 | 0 | 0 | [52 empty] | 176 | Principal |  |  | 1 | 2
2642 | Saltmarsh Terrace | Active | KJ | 0 | 0 | 0 | [52 empty] | 176 | Director |  |  | 1 | 3
2642 | Saltmarsh Terrace | Active | HL | 0 | 0 | 0 | [52 empty] | 176 | Senior Designer |  |  | 1 | 4
2642 | Saltmarsh Terrace | Active | EHH | 0 | 0 | 0 | [52 empty] | 176 | Mid Level Designer |  |  | 1 | 5
2642 | Saltmarsh Terrace | Active | KD | 0 | 0 | 0 | [52 empty] | 176 | Mid Level Designer |  |  | 1 | 6
2642 | Saltmarsh Terrace | Active | XX | 0 | 0 | 0 | [52 empty] | 176 | Project Designer |  |  | 1 | 7
2642 | Saltmarsh Terrace | Active |  |  | 0 | [53 empty] | 176 |  |  |  | 1 | 8
| 2672 · Marigold Plaza | Active |  | 1483 | 1458 | 25 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 100 | 100 | 84 | 84 | 84 | 84 | 84 | 84 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2672 | Marigold Plaza | Active | PK | 150 | 144 | 6 | 2026-10-05: 16; 2026-10-12: 16; 2026-10-19: 16; 2026-10-26: 16; 2026-11-02: 16; 2026-11-09: 16; 2026-11-16: 16; 2026-11-23: 16; 2026-11-30: 16 | 184 | Principal | 2026-10-05 | 2030-01-01 | 1 | 1
2672 | Marigold Plaza | Active | DF | 270 | 256 | 14 | 2026-10-05: 16; 2026-10-12: 16; 2026-10-19: 16; 2026-10-26: 16; 2026-11-02: 16; 2026-11-09: 16; 2026-11-16: 16; 2026-11-23: 16; 2026-11-30: 16; 2026-12-07: 16; 2026-12-14: 16; 2026-12-21: 16; 2026-12-28: 16; 2027-01-04: 16; 2027-01-11: 16; 2027-01-18: 8; 2027-01-25: 8 | 184 | Principal | 2026-10-05 | 2030-01-01 | 1 | 2
2672 | Marigold Plaza | Active | KJ | 120 | 120 | 0 | 2026-11-23: 12; 2026-11-30: 12; 2026-12-07: 12; 2026-12-14: 12; 2026-12-21: 12; 2026-12-28: 12; 2027-01-04: 12; 2027-01-11: 12; 2027-01-18: 12; 2027-01-25: 12 | 184 | Director | 2026-10-05 | 2030-01-01 | 1 | 3
2672 | Marigold Plaza | Active | HL | 333 | 328 | 5 | 2026-10-05: 24; 2026-10-12: 24; 2026-10-19: 24; 2026-10-26: 24; 2026-11-02: 24; 2026-11-09: 24; 2026-11-16: 24; 2026-11-23: 16; 2026-11-30: 16; 2026-12-07: 16; 2026-12-14: 16; 2026-12-21: 16; 2026-12-28: 16; 2027-01-04: 16; 2027-01-11: 16; 2027-01-18: 16; 2027-01-25: 16 | 184 | Senior Designer | 2026-10-05 | 2030-01-01 | 1 | 4
2672 | Marigold Plaza | Active | EHH | 0 | 0 | 0 | [52 empty] | 184 | Mid Level Designer | 2026-10-05 | 2030-01-01 | 1 | 5
2672 | Marigold Plaza | Active | KD | 0 | 0 | 0 | [52 empty] | 184 | Mid Level Designer | 2026-10-05 | 2030-01-01 | 1 | 6
2672 | Marigold Plaza | Active | XX | 610 | 610 | 0 | 2026-10-05: 30; 2026-10-12: 30; 2026-10-19: 30; 2026-10-26: 30; 2026-11-02: 30; 2026-11-09: 30; 2026-11-16: 30; 2026-11-23: 40; 2026-11-30: 40; 2026-12-07: 40; 2026-12-14: 40; 2026-12-21: 40; 2026-12-28: 40; 2027-01-04: 40; 2027-01-11: 40; 2027-01-18: 40; 2027-01-25: 40 | 184 | Project Designer | 2026-10-05 | 2030-01-01 | 1 | 7
2672 | Marigold Plaza | Active |  |  | 0 | [53 empty] | 184 |  | 2026-10-05 | 2030-01-01 | 1 | 8
| 2673 · Meadow Townhomes | Active |  | 572 | 148 | 424 | 37 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2673 | Meadow Townhomes | Active | PK | 61 | 32 | 29 | 2026-10-05: 8; 2026-10-12: 8; 2026-10-19: 8; 2026-10-26: 8 | 189 | Principal | 2026-10-05 | 2028-09-02 | 1 | 1
2673 | Meadow Townhomes | Active | DF | 0 | 0 | 0 | [52 empty] | 189 | Principal | 2026-10-05 | 2028-09-02 | 1 | 2
2673 | Meadow Townhomes | Active | KJ | 107 | 0 | 107 | [52 empty] | 189 | Director | 2026-10-05 | 2028-09-02 | 1 | 3
2673 | Meadow Townhomes | Active | HL | 44 | 48 | -4 | 2026-10-05: 12; 2026-10-12: 12; 2026-10-19: 12; 2026-10-26: 12 | 189 | Senior Designer | 2026-10-05 | 2028-09-02 | 1 | 4
2673 | Meadow Townhomes | Active | EHH | 4 | 4 | 0 | [52 empty] | 189 | Mid Level Designer | 2026-10-05 | 2028-09-02 | 1 | 5 | bar: 2026-10-05 to 2026-10-26
2673 | Meadow Townhomes | Active | KD | 356 | 64 | 292 | 2026-10-05: 16; 2026-10-12: 16; 2026-10-19: 16; 2026-10-26: 16 | 189 | Mid Level Designer | 2026-10-05 | 2028-09-02 | 1 | 6
2673 | Meadow Townhomes | Active | XX | 0 | 0 | 0 | [52 empty] | 189 | Project Designer | 2026-10-05 | 2028-09-02 | 1 | 7
2673 | Meadow Townhomes | Active |  |  | 0 | [53 empty] | 189 |  | 2026-10-05 | 2028-09-02 | 1 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PK | [56 empty] | Principal |  |  | 0 | 1
|  |  | DF | [56 empty] | Principal |  |  | 0 | 2
|  |  | KJ | [56 empty] | Director |  |  | 0 | 3
|  |  | HL | [56 empty] | Senior Designer |  |  | 0 | 4
|  |  | EHH | [56 empty] | Mid Level Designer |  |  | 0 | 5
|  |  | KD | [56 empty] | Mid Level Designer |  |  | 0 | 6
|  |  | XX | [56 empty] | Project Designer |  |  | 0 | 7
[63 empty] | 0 | 8

## Forecast
52-Week Demand vs. Capacity Forecast
Scenario: Active + Prospective (prospective weighted at 100%) ¦ Weeks begin Monday. Everything here is formula-driven — edit Projects or Assumptions.
Week # |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Week Beginning (Mon) | 52-Wk Avg | Peak / Worst | time axis 2026-10-05 to 2027-09-27
1. HOURS ASSIGNED PER WEEK — by staff member. Red = over their allocated hours, green = within
PK · Principal | 11.1538 | 61 | 56 | 60 | 53 | 61 | 45 | 37 | 29 | 29 | 28 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 12 | 8 | 8 | 12 | 16 | 16 | 20 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DF · Principal | 9.9615 | 34 | 26 | 26 | 26 | 34 | 34 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 16 | 16 | 8 | 16 | 16 | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KJ · Director | 11.8654 | 38 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 38 | 38 | 23 | 23 | 15 | 15 | 15 | 30 | 28 | 36 | 24 | 9 | 9 | 9 | 9 | 9 | 5 | 1 | 1 | 5 | 5 | 5 | 5 | 20 | 20 | 20 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HL · Senior Designer | 9.0769 | 52 | 52 | 52 | 52 | 52 | 40 | 40 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EHH · Mid Level Designer | 3.4615 | 16 | 1 | 1 | 1 | 9 | 8 | 8 | 8 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KD · Mid Level Designer | 10.9231 | 56 | 40 | 56 | 56 | 56 | 40 | 36 | 40 | 40 | 40 | 20 | 20 | 0 | 0 | 0 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
XX · Project Designer | 15.1923 | 60 | 38 | 38 | 46 | 46 | 38 | 38 | 38 | 56 | 56 | 40 | 40 | 44 | 40 | 40 | 48 | 60 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total hours assigned | 71.6346 | 284 | 231 | 259 | 260 | 284 | 231 | 211 | 191 | 213 | 212 | 153 | 153 | 125 | 121 | 121 | 160 | 160 | 172 | 76 | 33 | 37 | 41 | 41 | 37 | 5 | 1 | 1 | 7 | 7 | 7 | 7 | 46 | 42 | 42 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. ALLOCATED HOURS PER WEEK — each person's available billable hours (FTE × hours × target utilization)
PK · Principal | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
DF · Principal | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
KJ · Director | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
HL · Senior Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
EHH · Mid Level Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
KD · Mid Level Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
XX · Project Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Total allocated hours (capacity) | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236
3. OVER / (UNDER) ALLOCATED HOURS — assigned minus allocated. Red = over, green = under
PK · Principal | -18.8462 | 31 | 26 | 30 | 23 | 31 | 15 | 7 | -1 | -1 | -2 | -18 | -18 | -22 | -22 | -22 | -22 | -22 | -18 | -22 | -22 | -18 | -14 | -14 | -10 | -30 | -30 | -30 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30
DF · Principal | -20.0385 | 4 | -4 | -4 | -4 | 4 | 4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -4 | -14 | -14 | -22 | -14 | -14 | -14 | -14 | -22 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30
KJ · Director | -20.1346 | 6 | -14 | -6 | -6 | -6 | -6 | -6 | -6 | 6 | 6 | -9 | -9 | -17 | -17 | -17 | -2 | -4 | 4 | -8 | -23 | -23 | -23 | -23 | -23 | -27 | -31 | -31 | -27 | -27 | -27 | -27 | -12 | -12 | -12 | -28 | -28 | -28 | -28 | -28 | -28 | -30 | -32 | -32 | -32 | -32 | -32 | -32 | -32 | -32 | -32 | -32 | -32 | -32
HL · Senior Designer | -26.9231 | 16 | 16 | 16 | 16 | 16 | 4 | 4 | -12 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36
EHH · Mid Level Designer | -32.5385 | -20 | -35 | -35 | -35 | -27 | -28 | -28 | -28 | -28 | -28 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -20 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36
KD · Mid Level Designer | -25.0769 | 20 | 4 | 20 | 20 | 20 | 4 | 0 | 4 | 4 | 4 | -16 | -16 | -36 | -36 | -36 | -20 | -20 | -20 | -20 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -16 | -16 | -16 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36
XX · Project Designer | -20.8077 | 24 | 2 | 2 | 10 | 10 | 2 | 2 | 2 | 20 | 20 | 4 | 4 | 8 | 4 | 4 | 12 | 24 | 24 | -16 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -32 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36 | -36
Firm net over / (under) hours | -164.3654 | 48 | -5 | 23 | 24 | 48 | -5 | -25 | -45 | -23 | -24 | -83 | -83 | -111 | -115 | -115 | -76 | -76 | -64 | -160 | -203 | -199 | -195 | -195 | -199 | -231 | -235 | -235 | -229 | -229 | -229 | -229 | -190 | -194 | -194 | -230 | -230 | -230 | -230 | -230 | -230 | -234 | -236 | -236 | -236 | -236 | -236 | -236 | -236 | -236 | -236 | -236 | -236 | -236
4. FIRM UTILIZATION & HIRE SIGNAL
Firm utilization (assigned ÷ allocated) | 30.35% | 120.3% | 97.88% | 109.7% | 110.2% | 120.3% | 97.88% | 89.41% | 80.93% | 90.25% | 89.83% | 64.83% | 64.83% | 52.97% | 51.27% | 51.27% | 67.8% | 67.8% | 72.88% | 32.2% | 13.98% | 15.68% | 17.37% | 17.37% | 15.68% | 2.119% | 0.4237% | 0.4237% | 2.966% | 2.966% | 2.966% | 2.966% | 19.49% | 17.8% | 17.8% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 0.8475% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FTEs over (firm net overage ÷ avg hours per FTE) | 0.054188 | 1.4237 | 0 | 0.6822 | 0.71186 | 1.4237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HIRE SIGNAL (net overage ≥ hire trigger) | 3 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
First hire-signal week: 10/12/26 ¦ Trigger = 0.5 FTE of firm net overage (set on Assumptions)
Column B = 52-week average. Column C = peak / worst week. Red = over, green = under.
SUPPORTING DETAIL — BY STAFF LEVEL (feeds the Dashboard and Timeline heat map)
1. DEMAND — planned hours per week
Principal | 21.1154 | 95 | 82 | 86 | 79 | 95 | 79 | 63 | 55 | 55 | 54 | 38 | 38 | 34 | 34 | 34 | 34 | 24 | 28 | 16 | 24 | 28 | 32 | 32 | 28 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Director | 11.8654 | 38 | 18 | 26 | 26 | 26 | 26 | 26 | 26 | 38 | 38 | 23 | 23 | 15 | 15 | 15 | 30 | 28 | 36 | 24 | 9 | 9 | 9 | 9 | 9 | 5 | 1 | 1 | 5 | 5 | 5 | 5 | 20 | 20 | 20 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Designer | 9.0769 | 52 | 52 | 52 | 52 | 52 | 40 | 40 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid Level Designer | 14.3846 | 65 | 41 | 57 | 57 | 65 | 48 | 44 | 48 | 48 | 48 | 36 | 36 | 16 | 16 | 16 | 32 | 32 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Designer | 15.1923 | 60 | 38 | 38 | 46 | 46 | 38 | 38 | 38 | 56 | 56 | 40 | 40 | 44 | 40 | 40 | 48 | 60 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Demand | 71.6346 | 284 | 231 | 259 | 260 | 284 | 231 | 211 | 191 | 213 | 212 | 153 | 153 | 125 | 121 | 121 | 160 | 160 | 172 | 76 | 33 | 37 | 41 | 41 | 37 | 5 | 1 | 1 | 7 | 7 | 7 | 7 | 46 | 42 | 42 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. CAPACITY — available billable hours per week
Principal | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Director | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Senior Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Mid Level Designer | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Project Designer | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Total Capacity | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236
3. SURPLUS / (SHORTFALL) — capacity minus demand, hours
Principal | 38.8846 | -35 | -22 | -26 | -19 | -35 | -19 | -3 | 5 | 5 | 6 | 22 | 22 | 26 | 26 | 26 | 26 | 36 | 32 | 44 | 36 | 32 | 28 | 28 | 32 | 60 | 60 | 60 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Director | 20.1346 | -6 | 14 | 6 | 6 | 6 | 6 | 6 | 6 | -6 | -6 | 9 | 9 | 17 | 17 | 17 | 2 | 4 | -4 | 8 | 23 | 23 | 23 | 23 | 23 | 27 | 31 | 31 | 27 | 27 | 27 | 27 | 12 | 12 | 12 | 28 | 28 | 28 | 28 | 28 | 28 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Senior Designer | 26.9231 | -16 | -16 | -16 | -16 | -16 | -4 | -4 | 12 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Mid Level Designer | 57.6154 | 7 | 31 | 15 | 15 | 7 | 24 | 28 | 24 | 24 | 24 | 36 | 36 | 56 | 56 | 56 | 40 | 40 | 40 | 56 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 52 | 52 | 52 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Project Designer | 20.8077 | -24 | -2 | -2 | -10 | -10 | -2 | -2 | -2 | -20 | -20 | -4 | -4 | -8 | -4 | -4 | -12 | -24 | -24 | 16 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 32 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Total Surplus / (Shortfall) | 164.3654 | -48 | 5 | -23 | -24 | -48 | 5 | 25 | 45 | 23 | 24 | 83 | 83 | 111 | 115 | 115 | 76 | 76 | 64 | 160 | 203 | 199 | 195 | 195 | 199 | 231 | 235 | 235 | 229 | 229 | 229 | 229 | 190 | 194 | 194 | 230 | 230 | 230 | 230 | 230 | 230 | 234 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236 | 236
4. UTILIZATION — demand ÷ capacity
Principal | 35.19% | 158.3% | 136.7% | 143.3% | 131.7% | 158.3% | 131.7% | 105% | 91.67% | 91.67% | 90% | 63.33% | 63.33% | 56.67% | 56.67% | 56.67% | 56.67% | 40% | 46.67% | 26.67% | 40% | 46.67% | 53.33% | 53.33% | 46.67% | 0% | 0% | 0% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 3.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Director | 37.08% | 118.8% | 56.25% | 81.25% | 81.25% | 81.25% | 81.25% | 81.25% | 81.25% | 118.8% | 118.8% | 71.88% | 71.88% | 46.88% | 46.88% | 46.88% | 93.75% | 87.5% | 112.5% | 75% | 28.12% | 28.12% | 28.12% | 28.12% | 28.12% | 15.62% | 3.125% | 3.125% | 15.62% | 15.62% | 15.62% | 15.62% | 62.5% | 62.5% | 62.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 6.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Senior Designer | 25.21% | 144.4% | 144.4% | 144.4% | 144.4% | 144.4% | 111.1% | 111.1% | 66.67% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Mid Level Designer | 19.98% | 90.28% | 56.94% | 79.17% | 79.17% | 90.28% | 66.67% | 61.11% | 66.67% | 66.67% | 66.67% | 50% | 50% | 22.22% | 22.22% | 22.22% | 44.44% | 44.44% | 44.44% | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.78% | 27.78% | 27.78% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Project Designer | 42.2% | 166.7% | 105.6% | 105.6% | 127.8% | 127.8% | 105.6% | 105.6% | 105.6% | 155.6% | 155.6% | 111.1% | 111.1% | 122.2% | 111.1% | 111.1% | 133.3% | 166.7% | 166.7% | 55.56% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total Utilization | 30.35% | 120.3% | 97.88% | 109.7% | 110.2% | 120.3% | 97.88% | 89.41% | 80.93% | 90.25% | 89.83% | 64.83% | 64.83% | 52.97% | 51.27% | 51.27% | 67.8% | 67.8% | 72.88% | 32.2% | 13.98% | 15.68% | 17.37% | 17.37% | 15.68% | 2.119% | 0.4237% | 0.4237% | 2.966% | 2.966% | 2.966% | 2.966% | 19.49% | 17.8% | 17.8% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 2.542% | 0.8475% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5. FTE GAP — positive = FTEs short (hire); negative = spare FTEs
Principal | -1.2962 | 1.1667 | 0.73333 | 0.86667 | 0.63333 | 1.1667 | 0.63333 | 0.1 | -0.16667 | -0.16667 | -0.2 | -0.73333 | -0.73333 | -0.86667 | -0.86667 | -0.86667 | -0.86667 | -1.2 | -1.0667 | -1.4667 | -1.2 | -1.0667 | -0.93333 | -0.93333 | -1.0667 | -2 | -2 | -2 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -1.9333 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2
Director | -0.62921 | 0.1875 | -0.4375 | -0.1875 | -0.1875 | -0.1875 | -0.1875 | -0.1875 | -0.1875 | 0.1875 | 0.1875 | -0.28125 | -0.28125 | -0.53125 | -0.53125 | -0.53125 | -0.0625 | -0.125 | 0.125 | -0.25 | -0.71875 | -0.71875 | -0.71875 | -0.71875 | -0.71875 | -0.84375 | -0.96875 | -0.96875 | -0.84375 | -0.84375 | -0.84375 | -0.84375 | -0.375 | -0.375 | -0.375 | -0.875 | -0.875 | -0.875 | -0.875 | -0.875 | -0.875 | -0.9375 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
Senior Designer | -0.74786 | 0.44444 | 0.44444 | 0.44444 | 0.44444 | 0.44444 | 0.11111 | 0.11111 | -0.33333 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -0.55556 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
Mid Level Designer | -1.6004 | -0.19444 | -0.86111 | -0.41667 | -0.41667 | -0.19444 | -0.66667 | -0.77778 | -0.66667 | -0.66667 | -0.66667 | -1 | -1 | -1.5556 | -1.5556 | -1.5556 | -1.1111 | -1.1111 | -1.1111 | -1.5556 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -1.4444 | -1.4444 | -1.4444 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2
Project Designer | -0.57799 | 0.66667 | 0.055556 | 0.055556 | 0.27778 | 0.27778 | 0.055556 | 0.055556 | 0.055556 | 0.55556 | 0.55556 | 0.11111 | 0.11111 | 0.22222 | 0.11111 | 0.11111 | 0.33333 | 0.66667 | 0.66667 | -0.44444 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -0.88889 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
Total FTE Gap (net across levels) | -4.8516 | 1.5069 | -0.065278 | 0.7625 | 0.75139 | 1.5069 | -0.054167 | -0.69861 | -1.2986 | -0.64583 | -0.67917 | -2.459 | -2.459 | -3.2868 | -3.3979 | -3.3979 | -2.2625 | -2.325 | -1.9417 | -4.7167 | -5.9188 | -5.7854 | -5.6521 | -5.6521 | -5.7854 | -6.8438 | -6.9688 | -6.9688 | -6.7771 | -6.7771 | -6.7771 | -6.7771 | -5.6417 | -5.7528 | -5.7528 | -6.8083 | -6.8083 | -6.8083 | -6.8083 | -6.8083 | -6.8083 | -6.9375 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7
6. SIGNALS — levels flagged | Total | Max
# Levels understaffed | 32 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# Levels with excess capacity | 200 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Legend
Red = understaffed (demand above capacity / FTE gap at or above hire trigger)
Amber = excess capacity (utilization below threshold) or small FTE gap under trigger
Green = utilization within target band

## Economics
Project Economics — planned hours, projected cost & fee
Covers full phase durations (not limited to the 52-week window) and all rows on the Projects sheet, unweighted. Projected cost = planned hours × rates on Assumptions.
PORTFOLIO SUMMARY BY STATUS
Status |  | Phases | Planned Hours | Projected Cost ($) | Phase Fee ($) | Fee vs Cost ($) | % of Fee Used
Active |  | 43 | 5330.5 | 1098015 | 2591500 | 1493485 | 42.37%
Prospective |  | 0 | 0 | 0 | 0 | 0
Inactive |  | 5 | 0 | 0 | 127500 | 127500 | 0%
Total (active + prospective) |  | 43 | 5330.5 | 1098015 | 2591500 | 1493485 | 42.37%
BY STAFF LEVEL (all phases & statuses)
Staff Level |  | Billable Rate ($/hr) | Planned Hours | Projected Cost ($) | % of Cost
Principal |  | 290 | 1298.5 | 376565 | 34.3%
Director |  | 250 | 775 | 193750 | 17.65%
Senior Designer |  | 200 | 509 | 101800 | 9.271%
Mid Level Designer |  | 175 | 1373 | 240275 | 21.88%
Project Designer |  | 135 | 1375 | 185625 | 16.91%
Total / blended rate |  | 205.9872 | 5330.5 | 1098015 | 100%
BY PROJECT (auto-listed from the Projects sheet)
Project No. | Project Name | Status | Phases | First Start | Last End | Planned Hours | Projected Cost ($) | Phase Fee ($) | Fee vs Cost ($) | % of Fee Used | Flag
2256 | Marigold Promenade | Active | 1 | 2027-04-01 | 2027-10-05 | 81 | 21330 | 43500 | 22170 | 49.03% | OK
2348 | Fairhaven Senior Housing | Inactive | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2370 | Tamarack Housing | Inactive | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2458 | Summit Ridge Village | Inactive | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2469 | Fairhaven Village | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2470 | Canyon Vista Park | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2489 | Harbor Mobility Hub | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2494 | Laurel Park Garden | Active | 3 |  |  | 0 | 0 | 88000 | 88000 | 0% | No hours entered
2499 | Zephyr Creative Office | Active | 1 | 2026-10-12 | 2026-12-20 | 300 | 63100 | 76500 | 13400 | 82.48% | OK
2545 | Mariner Courtyard | Inactive | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2550 | Driftwood Park | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2551 | Bayside Community Center | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2560 | Willowmere Trail | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2562 | Pebble Creek Courtyard | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2570 | Saltmarsh Master Plan | Active | 4 | 2026-10-26 | 2027-03-12 | 1264 | 241400 | 128000 | -113400 | 188.6% | Fee below projected cost
2576 | Westbury Elementary School | Inactive | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2577 | Riverbend Master Plan | Active | 1 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2582 | Bayside Lofts | Active | 1 | 2026-02-01 | 2026-04-25 | 72 | 18480 | 23000 | 4520 | 80.35% | OK
2583 | Cypress Point Campus Plan | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2584 | Hollis Campus Plan | Active | 6 | 2026-10-05 | 2026-11-13 | 144 | 33120 | 111500 | 78380 | 29.7% | OK
2622 | Hawthorne Glen Senior Housing | Active | 3 | 2026-10-05 | 2027-10-31 | 970 | 209740 | 247500 | 37760 | 84.74% | OK
2626 | Northgate Courtyard | Active | 0 |  |  | 0 | 0 | 0 | 0 |  | No hours entered
2627 | Ridgeview Lofts | Active | 4 | 2026-10-05 | 2027-01-14 | 127.5 | 28800 | 98500 | 69700 | 29.24% | OK
2630 | Birch Roof Deck | Inactive | 5 |  |  | 0 | 0 | 127500 | 127500 | 0% | No hours entered
2636 | Stonebridge Streetscape | Active | 2 | 2026-10-05 | 2026-11-23 | 317 | 65055 | 127500 | 62445 | 51.02% | OK
2642 | Saltmarsh Terrace | Active | 7 |  |  | 0 | 0 | 404500 | 404500 | 0% | No hours entered
2672 | Marigold Plaza | Active | 4 | 2026-10-05 | 2030-01-01 | 1483 | 300750 | 1117500 | 816750 | 26.91% | OK
2673 | Meadow Townhomes | Active | 6 | 2026-10-05 | 2028-09-02 | 572 | 116240 | 125500 | 9260 | 92.62% | OK
Formulas:
Projected Cost ($) = IF([Status]="","",INDEX(pjStart,MATCH([Status],pjNo,0)))
Phase Fee ($) = IF([Status]="","",INDEX(pjEnd,MATCH([Status],pjNo,0)))