## Sheet1
2026 Master Schedule
|  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
|  | Status | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
Copperfield Terrace | 2106
Whitby Pavilion | 2117
Riverbend Creative Office | 2118
Tamarack Pavilion | 2120
Mariner Terrace | 2124
Northgate Trail | 2126
Riverbend Streetscape | 2129 | On Hold
Ridgeview Arts Center | 2142
Eastvale Residences | 2144
Sunset Mesa Elementary School | 2151
Oakhurst Plaza | 2154
Cedar Arts Center | 2158
Zephyr Townhomes | 2161
Redstone Senior Housing | 2163
Thornbury Pavilion | 2172
Clearwater Garden | 2175
Lakeshore Courtyard | 2176 | On Hold
Tamarack Lofts | 2177
Ironwood Community Center | 2178 | Concept | [6 empty] | Cost estimate review | Specifications |  | Plan check comments | Concept options
Marigold Housing | 2180
Thornbury Garden | 2187
Stonebridge Lofts | 2190
Bluebell Elementary School | 2194
Copperfield Pavilion | 2199
Thornbury Mobility Hub | 2202
Maple Hollow Courtyard | 2206
Sandpiper Streetscape | 2214
Tamarack Community Center | 2219
Whitby Roof Deck | 2231
Pinecrest Trail | 2232 | Construction | [10 empty] | 90% CD set (HL)
Orchard Trail | 2240
Thornbury Senior Housing | 2251
Sierra Creative Office | 2254
Marigold Promenade | 2256 | Construction | [9 empty] | Fee proposal | Fee proposal (PK) | Planting plan | Submittal review
Northgate Mobility Hub | 2258
Juniper Creative Office | 2259
Sandpiper Roof Deck | 2278
Kestrel Commons | 2283
Glenmoor Commons | 2286
Oakhurst Housing | 2289
Tamarack Commons | 2294
Sandpiper Plaza | 2297
Stonebridge Pavilion | 2304
Thornbury Trail | 2305
Pinecrest Master Plan | 2306
Hollis Village | 2309
Highcrest Creative Office | 2310
Harbor Community Center | 2319
Ashford Housing | 2320
Saltmarsh Village | 2326
Quarry Pavilion | 2327
Ironwood Courtyard | 2328
Coralwood Promenade | 2330
Thornbury Campus Plan | 2338
Fairhaven Senior Housing | 2348 | Construction | [6 empty] | Cost estimate review (HL)
n/a | 2354
Glenmoor Trail | 2355
Kestrel Village | 2358
Birch Promenade | 2361
Summit Ridge Creative Office | 2362
Fairhaven Creative Office | 2365
Larkspur Townhomes | 2368
Tamarack Housing | 2370 | In Permitting
Bluebell Community Center | 2382
Upland Village | 2393
Linden Elementary School | 2402 | Concept | [9 empty] | Lighting coordination (KD)
Maple Hollow Arts Center | 2409
Driftwood Housing | 2412
Zephyr Garden | 2419
Laurel Park Pavilion | 2425
Yarrow Streetscape | 2447
Juniper Terrace | 2452
Summit Ridge Village | 2458 | Construction | [6 empty] | SD package |  |  | Billing | Billing
Sierra Terrace | 2459 | Permitting/CA
Fairhaven Village | 2469A | SD |  | Plan check comments |  |  |  |  | Concept options |  |  |  | Client presentation
Fairhaven Village | 2469B | CA
Canyon Vista Park | 2470 | Construction | [10 empty] | Fee proposal
Linden Mobility Hub | 2471
Copperfield Elementary School | 2476
Glenmoor Pavilion | 2480
Orchard Commons | 2481
Harbor Campus Plan | 2483
Bluebell Campus Plan | 2488
Harbor Mobility Hub | 2489 | CD | 100% DD | [5 empty] | Planting plan |  |  |  | Specifications
Summit Ridge Townhomes | 2490 | SD
Coralwood Library | 2492 | Construction
Laurel Park Garden | 2494 | Construction | [6 empty] | Community meeting (HL) |  |  | Planting plan (PK) | Fee proposal | 100% DD | Lighting coordination |  |  |  |  | 100% CD set | Site visit |  | Billing |  |  | 50% DD (PK) | Submittal review
Mariner Library | 2497
Zephyr Creative Office | 2499 | CD | [9 empty] | Fee proposal | Plan check comments |  | Community meeting
Copperfield Garden | 2506
Saltmarsh Mobility Hub | 2516
Upland Terrace | 2528
Silverlake Row Senior Housing | 2529
Pinecrest Elementary School | 2534
Glenmoor Library | 2536 | Concept
Wren Master Plan | 2537 | Construction
Coralwood Mobility Hub | 2542
Mariner Courtyard | 2545 | SD
Whitby Arts Center | 2547
Driftwood Park | 2550 | In Permitting | [9 empty] | Design review (EHH)
Bayside Community Center | 2551 | SD | Submittal review | [5 empty] | 50% CD set (DF) |  | Renderings | Planting plan | Specifications | Kick-off meeting | Cost estimate review
Marigold Park | 2558
Willowmere Trail | 2560 | CDs | [9 empty] | Planting plan (KD)
Pebble Creek Courtyard | 2562 | CDs | [8 empty] | Client presentation | Submittal review | SD package | Punch list | [6 empty] | Design review (PK) |  |  |  | Specifications | 90% CD set
Ironwood Village | 2565
Saltmarsh Master Plan | 2570 | Concept | [6 empty] | Plan check comments |  |  | Fee proposal | Submittal review |  |  |  | Design review |  |  |  | Renderings (KD) | Concept options
Silverlake Row Garden | 2574
Westbury Elementary School | 2576 | Entitlement
Riverbend Master Plan | 2577 | CDs |  |  |  | Concept options (DF) | Fee proposal |  | Permit submission |  |  | Punch list (PK) | Site visit |  | Community meeting |  |  |  | Submittal review (PK)
Bayside Lofts | 2582 | Construction | [10 empty] | 50% CD set
Cypress Point Campus Plan | 2583 | SD | [10 empty] | Site visit (HL)
Hollis Campus Plan | 2584 | Concept | [6 empty] | Billing (KJ) |  |  | Renderings | Renderings |  |  | SD package
Riverbend Roof Deck | 2603
Wren Arts Center | 2611
Kestrel Master Plan | 2616
Hawthorne Glen Senior Housing | 2622 | SD |  |  |  | Lighting coordination |  |  | Specifications | Lighting coordination |  | Community meeting | Concept options | Bid set | Schedule update | Site visit | [5 empty] | 50% CD set
Northgate Courtyard | 2626 | CDs
Ridgeview Lofts | 2627 | DD | [9 empty] | 100% DD | Concept options | Cost estimate review |  |  |  | Client presentation |  |  |  | 50% DD (HL)
Birch Roof Deck | 2630 | SD |  |  | 50% CD set
Highcrest Courtyard | 2635 | Construction
Stonebridge Streetscape | 2636 | Concept | [8 empty] | Fee proposal | 100% CD set | Renderings
Saltmarsh Terrace | 2642 | Concept | [9 empty] | Client presentation (KJ) | Billing
Verdant Courtyard | 2646 | Concept | [6 empty] | Plan check comments |  |  |  | Client presentation | Concept options | Specifications
Marigold Plaza | [11 empty] | Planting plan | Site visit
Interior Campaign | [8 empty] | Permit submission | 50% CD set (HL) | Specifications | Lighting coordination
Fall Party | [9 empty] | Punch list (DF) |  | Consultant coordination (KD) |  | 50% CD set (EHH)
AA Website Refresh | 2672 | Concept | [6 empty] | 90% CD set |  |  | Community meeting |  | Permit submission (DF)
India Office | [8 empty] | 90% CD set (HL) | Permit submission (KJ) |  | Plan check comments
HR/Hiring | [8 empty] | 50% CD set |  | 90% CD set
BD/ Proposal | [11 empty] | Bid set (KJ) | Plan check comments
IT/ Software | [11 empty] | SD package (EHH)
Office Structure | [5 empty] | Fee proposal | Consultant coordination |  |  |  |  | 50% CD set (PK) | 90% CD set | Submittal review (EHH) | 100% CD set (KD) | 90% CD set (KD) | Site visit | 50% CD set (EHH) | Submittal review
Harper |  |  | Lead: Kestrel Village, Oakhurst Plaza Support: Thornbury Mobility Hub | Lead: Maple Hollow Arts Center, Birch Promenade Support: Marigold Plaza | Lead: Tamarack Lofts, Mariner Terrace Support: Saltmarsh Mobility Hub | Lead: Silverlake Row Garden, Upland Village Support: Sunset Mesa Elementary School | Lead: Ironwood Community Center, Copperfield Terrace Support: Redstone Senior Housing |  | Lead: Ironwood Courtyard, Zephyr Creative Office Support: Birch Promenade |  | Lead: Wren Master Plan, Cypress Point Campus Plan Support: Kestrel Village | Lead: Glenmoor Trail, Stonebridge Pavilion Support: Juniper Terrace | Lead: Verdant Courtyard, Zephyr Garden Support: Driftwood Park |  |  | 2026-11-09
Elliot |  |  | Lead: Northgate Trail, Canyon Vista Park Support: Bayside Lofts | Lead: Glenmoor Pavilion, Ironwood Village Support: Silverlake Row Garden | Lead: Wren Arts Center, Driftwood Housing Support: Redstone Senior Housing | Lead: Oakhurst Housing, Bluebell Campus Plan Support: Ridgeview Arts Center | Lead: Kestrel Commons, Summit Ridge Townhomes Support: Fairhaven Creative Office |  | Lead: Marigold Plaza, Oakhurst Housing Support: Sandpiper Roof Deck |  | Lead: Northgate Courtyard, Hollis Village Support: Birch Roof Deck | Lead: Lakeshore Courtyard, Bluebell Community Center Support: Birch Roof Deck | Lead: Driftwood Park, Clearwater Garden Support: Harbor Mobility Hub
Riley |  |  | Lead: Juniper Creative Office, Highcrest Courtyard Support: Redstone Senior Housing | Lead: Thornbury Campus Plan, Upland Terrace Support: Thornbury Garden | Lead: Glenmoor Commons, Sierra Creative Office Support: Birch Roof Deck | Lead: Zephyr Garden, Copperfield Terrace Support: Pebble Creek Courtyard | Lead: Laurel Park Garden, Bayside Community Center Support: Coralwood Promenade |  | Lead: Sandpiper Roof Deck, Maple Hollow Arts Center Support: Linden Elementary School |  | Lead: Coralwood Promenade, Coralwood Library Support: Thornbury Campus Plan | Lead: Stonebridge Pavilion, Eastvale Residences Support: Glenmoor Commons | Lead: Ashford Housing, Ridgeview Lofts Support: Laurel Park Garden | Lead: Glenmoor Pavilion, Canyon Vista Park Support: Whitby Arts Center
Parker |  |  | Lead: Cedar Arts Center, Thornbury Campus Plan Support: Summit Ridge Creative Office | OUT | OUT | Lead: Whitby Arts Center, Ironwood Community Center Support: Sandpiper Roof Deck | Lead: Lakeshore Courtyard, Canyon Vista Park Support: Linden Elementary School |  | Lead: Hollis Village, Tamarack Community Center Support: Ironwood Village |  | Lead: Ironwood Courtyard, Thornbury Mobility Hub Support: Saltmarsh Terrace | Lead: Canyon Vista Park, Mariner Terrace Support: Maple Hollow Courtyard | Lead: Copperfield Elementary School, Oakhurst Plaza Support: Kestrel Commons
Devon |  |  | OUT | Lead: Northgate Courtyard, Kestrel Commons Support: Bayside Lofts | Lead: Tamarack Housing, Coralwood Promenade Support: Mariner Courtyard | Lead: Riverbend Streetscape, Orchard Commons Support: Silverlake Row Senior Housing | Lead: Coralwood Library, Harbor Campus Plan Support: Verdant Courtyard |  | Lead: Highcrest Creative Office, Tamarack Housing Support: Riverbend Master Plan |  | Lead: Birch Roof Deck, Hawthorne Glen Senior Housing Support: Ironwood Courtyard | Lead: Eastvale Residences, Wren Master Plan Support: Driftwood Housing | Lead: Ridgeview Arts Center, Clearwater Garden Support: Pebble Creek Courtyard | Lead: Riverbend Roof Deck, Zephyr Townhomes Support: Juniper Creative Office | Lead: Northgate Trail, Mariner Terrace Support: Riverbend Streetscape | Lead: Stonebridge Lofts, Larkspur Townhomes Support: Pebble Creek Courtyard | Lead: Thornbury Garden, Kestrel Commons Support: Upland Village | Lead: Pinecrest Master Plan, Harbor Campus Plan Support: Whitby Pavilion
Sasha | [11 empty] | Lead: Ironwood Community Center, Zephyr Garden Support: Mariner Courtyard | Lead: Sierra Creative Office, Stonebridge Pavilion Support: Redstone Senior Housing
Blair | [5 empty] | Lead: Copperfield Elementary School, Bluebell Campus Plan Support: Sandpiper Plaza | Lead: Canyon Vista Park, Glenmoor Commons Support: Mariner Terrace | [5 empty] | Lead: Westbury Elementary School, Thornbury Garden Support: Glenmoor Commons